## Gantt Chart
Financial News Sentiment Analysis — Project Gantt Chart
IST 495 · Agentic AI Internship · May 5 – Aug 15, 2026 · 15 Weeks · Remote · 25 hrs/week
Task / Phase | May 2026 |  |  |  | June 2026 |  |  |  | July 2026 |  |  |  | August 2026
↓ Fill cells: Green = Done ¦ Red = Incomplete ¦ Yellow = In Progress | W1 May 5 | W2 May 12 | W3 May 19 | W4 May 26 | W5 Jun 2 | W6 Jun 9 | W7 Jun 16 | W8 Jun 23 | W9 Jun 30 | W10 Jul 7 | W11 Jul 14 | W12 Jul 21 | W13 Jul 28 | W14 Aug 4 | W15 Aug 11
PHASE 1 — SETUP & ARCHITECTURE (Weeks 1–2)
Python env + libraries (feedparser, requests, transformers, flask, crewai)
FinViz CSV download + ticker universe loader (pandas)
IBKR + TDA free account setup (news access only)
Architecture design: RSS → queue → FinBERT → Flask
◆ Milestone: Dev environment + sources confirmed |  | ◆
PHASE 2 — DATA INGESTION (Weeks 2–4)
RSS feed integration — 8 sources (feedparser + scheduling loop)
Web scraper — TradingView, FinViz, SEC EDGAR, FDA (BeautifulSoup)
IBKR + TDA news feed connection (free membership, basic API)
URL deduplication (Python set / hash index)
◆ Milestone: All data sources feeding into pipeline |  |  |  | ◆
PHASE 3 — TEXT PROCESSING & TICKER MATCHING (Weeks 4–6)
HTML stripping + English-only language filter
UTC timestamp normalization
Regex ticker extraction vs FinViz CSV ticker universe
Company name → ticker lookup table (manual + automated)
◆ Milestone: Clean, ticker-tagged articles in pipeline | [5 empty] | ◆
PHASE 4 — SENTIMENT ENGINE (Weeks 6–10)
FinBERT model setup + CPU batch inference (no GPU needed)
VADER fallback for low-confidence scores
CrewAI agent orchestration (Claude.ai / ChatGPT for complex articles)
Source trust weighting (Tier 1 = 1.0, Tier 2 = 0.75) + time-decay
◆ Milestone: Sentiment scores generated per article | [9 empty] | ◆
PHASE 5 — AGGREGATION & RANKING (Weeks 9–11)
Per-ticker weighted score aggregation (Python dict + SQLite)
Message density calculation (articles per hour per ticker)
Composite ranking (score × density sort)
◆ Milestone: Ranked ticker list from live data | [10 empty] | ◆
PHASE 6 — FLASK DASHBOARD (Weeks 11–14)
FinViz-style sortable table UI (Flask + Jinja2 template)
60-second auto-refresh (simple polling, no WebSocket needed)
Pop-up detail window (per-ticker sentiment score + article list)
◆ Milestone: Live dashboard running | [13 empty] | ◆
PHASE 7 — TESTING & DELIVERY (Weeks 13–15)
End-to-end latency test (target < 2 min pipeline)
Sentiment accuracy spot-checks + fixes
Code documentation + cleanup
Final demo to supervisor
◆ FINAL MILESTONE: Real-time pipeline < 2 min end-to-end (Aug 15, 2026) | [14 empty] | ◆
CONTINUOUS ACTIVITIES — All 15 Weeks
Weekly mentor meeting (required every week)
AI tools: Claude.ai, CrewAI, ChatGPT, Microsoft CoPilot, Gemini 3.1
Minimum 25 hrs/week · 250 hrs total target
COLOR KEY — Select any light-blue cell, then use Fill Color (Home tab) to mark your progress:
GREEN = Completed ✓ |  |  |  | RED = Incomplete / Behind |  |  |  | YELLOW = In Progress |  |  |  | Light Blue = Scheduled
◆ = milestone ¦ Grey = outside task scope ¦ Dark rows = phase headers ¦ Gold row = final deadline